## Slide 1
Hi! Show me today's stock
3 items · ₹1,240 · COD?
Share delivery location
Out for delivery · track
IMPLEMENTATION PLAN · VERSION 2.0
WhatsApp
Commerce Platform
A WhatsApp-first ordering, payment, and delivery system for retail — with in-chat location capture and live rider tracking.
20 weeks
to go-live
6 phases
+ parallel compliance track
26 tables
core data model
Prepared for management and engineering review · September 2026
Notes: Framing: this is a commerce platform with WhatsApp as the interface, not a chatbot. Two messages to land today: (1) the compliance track, not the code, is the critical path; (2) we are precise about what WhatsApp can and cannot do — which is why the location feature will actually ship.

## Slide 2
THE CASE
Why WhatsApp-first beats another app
01
Zero install friction
The customer orders inside an app they already open every day. No download, no signup, no password reset.
02
A conversation, not a checkout funnel
Guided menus collect intent step by step. There is no abandoned cart page to bounce from.
03
COD-native
Cash on delivery is a first-class path, not a bolt-on — matching how much of Indian retail actually pays.
04
Re-engagement is built in
Approved templates put order updates directly in the customer's chat list, where they are actually read.
The value is not the chatbot. It is the backend behind it — orders, payments, logistics, and operations.
2
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Deliberately no market-size statistics here — nothing in this deck is a number we cannot source. The four points are structural advantages of the channel, not claims about adoption.

## Slide 3
SCOPE
What version one actually ships
Catalogue browsing
Categories, products, images and stock, presented as WhatsApp lists and buttons.
Cart & order capture
Guided quantity selection, cart confirmation, and draft-to-final order conversion.
Location pin capture
In-chat location request, reverse geocoding, landmark notes, serviceability check.
COD + payment links
Cash on delivery with eligibility rules, or a secure expiring payment link.
Fulfilment & tracking
Shipment booking, normalised courier states, rider assignment, live tracking page.
Admin operations panel
Orders, products, manual overrides, resends, pin correction, and reporting.
Deliberately out of v1
Free-form AI shopping · loyalty wallet · automated returns engine · multi-vendor marketplace · marketing automation · multi-rider route optimisation · native in-chat payments
3
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Structured menus over free-form AI is a deliberate call: safer, faster to deliver, easier to test, and far more reliable in live retail operations. AI can be layered on later once real orders are flowing.

## Slide 4
HOW IT FEELS TO THE CUSTOMER
Six stages, start to doorstep
1
Opt in & greet
Consent captured and logged with wording and timestamp.
2
Browse & build cart
Categories, products, quantities — all interactive.
3
Share location
Tap once. Pin plus landmark, validated against service area.
4
Choose payment
COD if eligible, or a secure expiring payment link.
5
Order confirmed
Stock reserved with an expiry; confirmation sent.
6
Track to the door
Status templates plus a live rider tracking link.
Stages 1–5 happen inside the 24-hour service window — free-form, interactive, and cheap. Stage 6 almost always falls outside it — so every post-order update must be a pre-approved template. That single rule shapes the whole messaging design.
4
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Stage 3 is highlighted because it is the new capability in v2 and the one that most improves delivery success. Everything before it is standard conversational commerce.

## Slide 5
ARCHITECTURE
How the system is put together
CUSTOMER CHANNEL
Customer on WhatsApp
Catalogue, buttons, location
WhatsApp Cloud API
Webhooks · templates
OUR PLATFORM
API · NestJS
Worker · BullMQ
Geo Service
Admin Panel
Rider PWA
Tracking Page
DATA LAYER
PostgreSQL + PostGIS
Redis
Object Storage
Queues · retries · dead-letter · idempotency
EXTERNAL PROVIDERS
Razorpay
Payment links, callbacks
Shiprocket / Delhivery
Shipments, AWB, status
Maps platform
Geocoding, tracking map
Every provider sits behind an interface — WhatsAppProvider, PaymentProvider, LogisticsProvider, GeoProvider. Swap the courier, the gateway, or the BSP without touching business logic.
5
WhatsApp Commerce Platform · Implementation Plan v2
Notes: The provider-isolation rule is what makes 'we can swap the courier' a true statement rather than a sales line. No business logic imports a vendor SDK directly.

## Slide 6
MECHANICS
What happens when a customer sends a message
1
Receive
The message hits POST /webhooks/whatsapp. We verify the payload signature, store the raw event for replay, and acknowledge in under 500 ms.
Signature verified · raw event stored
2
Route
Session state is loaded from Redis. The reply is mapped to a flow step — browsing, cart update, location capture, or checkout.
Session TTL 30 min · cart survives
3
Act
Business logic runs: validate product and price, reserve stock with an expiry, check serviceability against the delivery pin, create the order.
Guarded state transitions · audit logged
4
Reply
If the 24-hour window is open we answer free-form. If it is closed, a free-form send is rejected at the service boundary and queued as a template instead.
Window checked before every send
5
Notify
Workers fire approved templates on fulfilment transitions, with retries, dead-letter handling, and a delivery receipt recorded per send.
Retryable · idempotent · observable
Every inbound event is stored raw and replayable. Every outbound send is tracked to a delivery outcome.
6
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Step 4 is the one engineers should note: window state is enforced in our own service layer, so an illegal free-form send fails fast in our code rather than surfacing as a provider error in production.

## Slide 7
THE CONSTRAINT THAT SHAPES EVERYTHING
The 24-hour service window
INSIDE THE WINDOW
Free-form. Anything goes.
Interactive menus and buttons
Location requests and location messages
Images, documents, free text
No template approval needed
Opened by the customer messaging us; any reply extends it
OUTSIDE THE WINDOW
Approved templates only.
Pre-approved by Meta, per template, per language
Billed per message — a recurring per-order cost
Requires demonstrable customer opt-in
No free-form replies, no raw location messages
This is where every post-order update lives
Design implication: complete every conversation inside the window, and consolidate post-order notifications. This is a cost decision as much as a UX one — every avoidable template send is a recurring charge on every order.
7
WhatsApp Commerce Platform · Implementation Plan v2
Notes: This slide did not exist in v1 of the plan and is the single most important addition. Nearly every downstream design decision — messaging, cost, the tracking approach — follows from this rule.

## Slide 8
DELIVERY PRECISION
Location in WhatsApp: what is real
Capability | Direction | Supported | What it means for us
Location request message | Business → customer | Yes | A tappable “Send location” button in the checkout flow
Location message from customer | Customer → business | Yes | Webhook returns latitude and longitude; address only if the pin maps to a known place
Location message to customer | Business → customer | Window only | Free-form, so unavailable once the 24-hour window has closed
Continuous live-location streaming | — | Not available | Not a documented Business Platform capability — we must not promise it
So here is the honest design
We capture an accurate one-shot delivery pin in chat — which is the part that actually improves delivery success. Live rider movement runs on our own tracking page, opened from an approved WhatsApp template. Designed this way the feature ships. Promised as “live location inside WhatsApp”, it fails at UAT.
8
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Verified against Meta's developer documentation. Item 5 of the Phase 0 checklist re-tests the live-streaming assumption before build starts, in case the platform adds it.

## Slide 9
DELIVERY PRECISION
How live tracking actually works
Rider PWA
GPS every
10–15 s
Redis
Hot position
cache
PostgreSQL
Sampled trail
30-day purge
Signed token
Short-lived,
single order
Tracking page
Map, ETA,
masked contact
The customer never sees any of that. They get one WhatsApp message.
Your order #4821 is out for delivery.
Rahul is on the way · arriving in about 18 minutes
Track my order
Approved template + URL button
SAFEGUARDS
Token dies the moment the order is delivered
Rider numbers are masked on the tracking page
GPS is collected only during an active trip
Last-known position is always shown with its timestamp
9
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Rider pings go to Redis for hot reads and only sampled writes to Postgres — writing every ping to the database would be needless write load. Location is sensitive personal data, hence the 30-day purge and the masking.

## Slide 10
DELIVERY PRECISION
The pin does more than help the rider
1
Serviceability by polygon
A spatial containment check against real delivery boundaries, instead of a PIN-code list that straddles serviceable and non-serviceable streets.
2
Enforceable COD rules
Cash on delivery restricted by area, order value, and product type — the rule finally has data to run against.
3
Distance-based delivery fees
Fee bands computed from the actual distance between the shop and the doorstep.
4
Address de-duplication
A new pin within about 25 metres of a saved address is treated as the same address, keeping repeat ordering clean.
5
Mis-pin and fraud flag
A pin implausibly far from the stated PIN code is held for manual review before dispatch.
The gap this closes
Version 1 of the plan said “restrict COD by PIN code” — with no data anywhere in the model to restrict against. The pin makes the rule enforceable.
Always with a fallback. Some customers will refuse the location permission or drop the wrong pin. A typed-address route that forward-geocodes to coordinates is mandatory — the checkout flow must never dead-end on a denied permission.
10
WhatsApp Commerce Platform · Implementation Plan v2
Notes: The fallback matters operationally — in testing, permission refusal is common enough that a flow without a typed route would strand a meaningful share of orders.

## Slide 11
DATA DESIGN
One order, three independent statuses
payment_status
not_required
pending
link_sent
paid
refund_pending
refunded
fulfillment_status
unfulfilled
confirmed
packed
shipped
out_for_delivery
delivered
order_status
draft
placed
confirmed
completed
cancelled
A cash-on-delivery order ships unpaid. That is exactly why these cannot be one enum. Version 1 defined two contradictory status lists in two different sections; v2 replaces both with three independent fields, and the label the customer sees is computed from them — never stored as a fourth source of truth.
11
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Every transition is guarded — illegal transitions raise rather than silently no-op — and each one writes to an immutable order_status_history row with actor and reason.

## Slide 12
DATA DESIGN
Twenty-six tables, six domains
4
Catalogue & stock
products · variants · inventory · reservations
3
Customers
customers · consents · addresses
5
Orders & money
carts · orders · order_items · payments · refunds
6
Fulfilment & delivery
service_areas · shipments · shipment_events · rider_assignments · rider_pings · tracking_links
3
Conversation
sessions · messages · message_templates
5
Platform & audit
webhook_events · idempotency_keys · status_history · staff_users · audit_log
NON-NEGOTIABLE DESIGN RULES
Money as integer paise — never floats
Price, tax and title snapshotted onto order lines
GST and HSN modelled from day one
Every stock reservation carries an expiry
Coordinates as PostGIS points, not loose floats
Every external write carries an idempotency key
12
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Tax is the one to flag to the team: GST and HSN are mandatory for Indian retail invoicing, and retrofitting them after checkout is built is expensive. They are in the Phase 1 schema for that reason.

## Slide 13
MONEY
Two payment paths, one set of rules
₹
Cash on delivery
Lowest-friction path — the order is placed immediately
Eligibility enforced by service area, order value and product type
Ships while payment_status stays not_required
→
Online payment link
A secure link scoped to one order, with an automatic expiry
Signature-verified gateway callback is the only proof of payment
Staff can re-issue a link from the admin panel at any time
RULES THAT PROTECT THE BUSINESS
No order reaches paid without a verified callback or an explicit, audited admin approval
Retries never overwrite each attempt is a new row, so the payment history stays intact
Links expire on a configurable timer, and can be re-sent rather than reopened
Refunds are records reconciled against the gateway and confirmed to the customer by template
Native in-chat payments stay deferred until confirmed available and approved for this account and region.
13
WhatsApp Commerce Platform · Implementation Plan v2
Notes: The 'no order reaches paid without a verified callback' rule is the one that prevents the classic failure mode: treating a client-side redirect as proof of payment.

## Slide 14
THE PAYOFF
What the business gets
Fewer failed deliveries
A coordinate pin plus a landmark replaces guesswork on unreliable typed addresses.
Lower support load
Customers self-serve order status and tracking in the chat they already have open.
No acquisition friction
Nothing to install, nothing to sign up for. The channel is already on the phone.
Real operational control
Every order, payment, shipment and message visible and correctable in one panel.
Provider independence
Courier, gateway, and messaging provider can each be replaced without a rewrite.
Auditable by design
Immutable status history, raw event storage, and a reason logged on every override.
< 500 ms
webhook ack, p95
99.5%
monthly uptime target
4
provider integrations
10
templates per language
14
WhatsApp Commerce Platform · Implementation Plan v2
Notes: These four numbers are commitments from the plan — service level objectives and integration counts — not market projections. If anyone asks for conversion or revenue uplift figures, those need real baseline data from the shop, which we do not have yet.

## Slide 15
ECONOMICS
What each order actually costs to serve
Cost driver | Charged on | The lever we control
WhatsApp templates | Per message sent, per market | Consolidate notifications; finish conversations inside the free window
Payment gateway | Percentage of prepaid order value | Encourage COD where margin is better; negotiate rate at volume
Courier | Per shipment, by weight and zone | Zone-aware fee banding using the delivery pin
Geocoding | Per address lookup | Geocode once per address and cache; never per page view
Tracking map loads | Per map render | Poll position data, not the map — the map loads once
The one insight worth remembering: messages inside the 24-hour window are the cheap path. Designing conversations to complete inside it is a cost decision, not just a user-experience one.
No rupee figures here on purpose — messaging rates, gateway percentages and courier slabs all need confirming against current provider pricing in Phase 0 before we quote anything. Fixed monthly costs sit on top: hosting for the API, worker, admin, Postgres and Redis, plus object storage, error tracking, and domain and TLS.
15
WhatsApp Commerce Platform · Implementation Plan v2
Notes: If the manager pushes for a per-order rupee number today, the honest answer is that it needs one week of Phase 0 to source current rates. Quoting an invented figure here is how projects get priced into a loss.

## Slide 16
DELIVERY
Twenty weeks, six phases, one parallel track
W1
W3
W5
W7
W9
W11
W13
W15
W17
W19
Track A · Compliance
W1–6
critical path
Phase 0 · Discovery
W1–2
Phase 1 · Foundation
W2–4
Phase 2 · Catalogue & flow
W4–7
Phase 3 · Location & payment
W7–11
Phase 4 · Fulfilment & tracking
W11–15
Phase 5 · Admin hardening
W15–17
Phase 6 · QA, UAT & go-live
W17–20
Track A runs from day one, in parallel with everything. All ten templates are submitted by week two, so rejections surface in week three while there is still time to fix them.
16
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Estimates assume one backend engineer, one frontend engineer, and part-time QA. If the shop uses couriers only and not its own riders, Phase 4 shortens by roughly a week because the rider PWA drops out of scope.

## Slide 17
THE RISK NOBODY PLANS FOR
The critical path is paperwork, not code
Meta business verification
Documents and business proof
1–3 weeks
Client + us
Display name approval
Can be rejected on wording
2–7 days
Client
Template approval
Per template, per language, ten of them
1–3 days each
Us
Payment gateway KYC
Merchant onboarding
1–2 weeks
Client
Courier account
Contract and API credentials
1–2 weeks
Client
Every one of these is external, slow, and capable of rejection. None of them can be sprinted. If they start in week one, we ship in twenty weeks; if they start when the code is ready, the date is anyone's guess.
17
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Ask for one thing at the end of this slide: a named owner on the client side for the verification documents, confirmed this week.

## Slide 18
RISK
What could go wrong, and what we do about it
Risk | Impact | Mitigation
Meta verification or template rejection | Go-live blocked | Track A starts week one; all templates in by week two; spare copy variants ready
Customer denies location permission | Checkout dead-ends | Mandatory typed-address fallback that forward-geocodes to coordinates
Client expects live location inside WhatsApp | Expectation gap at UAT | Capability documented now; tracking-page approach agreed in writing at kickoff
Rider GPS drops or app is backgrounded | Tracking gaps | Show last-known position with its timestamp; never render a stale pin as current
Duplicate provider webhooks | Duplicate orders or corrupt status | Idempotency keys plus raw event storage and replay
Messaging tier cap hit at launch | Customers unreachable | Model launch volume against the starting tier; monitor quality rating daily
The third row is the one to settle today — it is an expectation risk, not a technical one, and it is cheapest to fix before anyone has promised a client a moving dot inside WhatsApp.
18
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Keep this slide short in the room. The detail lives in the plan document; here we just want agreement that the mitigations are owned.

## Slide 19
OVER TO YOU
Six decisions we need before build starts
1
Direct Cloud API, or go through a BSP?
Changes per-message cost, template workflow, and how much we build ourselves.
Recommend direct, isolated behind an interface.
2
Own riders, a courier partner, or both?
The rider app and live tracking only exist if the shop runs its own last mile.
Roughly one week of Phase 4 depends on this.
3
Which languages need templates?
Every template needs separate approval per language.
Hindi or regional support doubles the approval workload.
4
What are the COD limits?
Ceiling by value, restricted categories, and excluded areas.
Needed before the eligibility rules can be written.
5
Who draws the delivery boundaries?
We need service areas as polygons, not a list of PIN codes.
A map exercise with the operations team.
6
Expected order volume at launch?
Determines whether the starting messaging tier is sufficient.
Also drives hosting sizing.
Decisions one and two are blocking — everything else can be answered during Phase 0 discovery.
19
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Land the meeting on these. If we leave with answers to one and two, and an owner for the verification paperwork, Phase 0 can start on Monday.

## Slide 20
IN CLOSING
Two things decide
whether this works
01
The compliance track is the critical path
Verification and template approval are external, slow, and can be rejected. Starting them in week one is the difference between a twenty-week delivery and an open-ended one.
02
Be precise about what the platform can do
Capturing a delivery pin in chat is fully supported and genuinely improves delivery success. Streaming live location inside WhatsApp is not. Designed honestly, the feature ships; promised loosely, it fails at UAT.
NEXT STEPS
1
Answer the two blocking decisions
BSP or direct, and whether the shop runs its own riders.
2
Name an owner for verification
Someone on the client side who can produce business documents this week.
3
Book the Phase 0 discovery session
Two weeks, with the operations team in the room to draw service areas.
4
Freeze and submit the template list
All ten, in every language we need, by the end of week two.
Full detail in the implementation plan — architecture, data model, API surface, testing plan, and the Phase 0 checklist.
20
WhatsApp Commerce Platform · Implementation Plan v2
Notes: Close by asking for the two decisions and the verification owner. Everything else can follow in Phase 0.